## Project Planner
Project Planner for Bike Sharing
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 20 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS in DAYS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
A | 1 | 20 | 1 | 20 | 100%
B | 2 | 2 | 2 | 2 | 100%
C | 4 | 1 | 4 | 3 | 100%
D | 5 | 2 | 7 | 2 | 100%
E | 7 | 2 | 9 | 2 | 100%
F | 9 | 1 | 11 | 2 | 100%
G | 10 | 4 | 13 | 1 | 100%
H | 14 | 3 | 14 | 3 | 100%
I | 17 | 2 | 17 | 1 | 100%
J | 19 | 1 | 18 | 2 | 100%
K | 20 | 1 | 20 | 1 | 100%
Note:
A - Business understanding
A.1 - Identify the objectives of the business and/or situation
A.2 - Access the situation
A.3 - Determine data mining objectives
A.4 - Project a project plan
B - Data understand
B.1 - Collect initial data
B.2 - Describe the data
B.3 - Explore the data
B.4 - Verify the data quality
C - Data preparation
C.1 - Select the data
C.2 - Clean the data
C.3 - Construct the data
C.4 - Integrate various data sources
C.5 - Format the data as required
D - Data transformation
D.1 - Reduce the data
D.2 - Project the data
E - Data-mining methods selection
E.1 - Match and discuss the objectives of data mining (A.1) to data mining methods
E.2 - Select the appropriate data-mining methods based on discussion
F - Data-mining algorithm selection
F.1 - Conduct exploratory analysis and discuss
F.2 - Select data-mining algorithms based on discussion
F.3 - Build/Select appropriate models and choose relevant parameters
G - Data mining
G.1 - Create and justify test designs
G.2 - Conduct data mining - classify, regress, cluster, etc.
G.3 - Search for patterns
H - Interpretation
H.1 - Study and discuss the mined patterns
H.2 - Visualize the data, results, models, and patterns
H.3 - Interpret the results, models, and patterns
H.4 - Assess and evaulate results, models, and patterns
H.5 - Iterate prior steps as required
I - Feedback and refinement
I.1 - Look for other peers to check any thing can be improved
I.2 - Look for tutor to check any thing can be improved
I.3 - Refine the report and make improvement as required
J - Action
J.1 - Discuss how you would apply the knowledge and deploy the implementation
J.2 - Discuss how you would monitor the implementation
J.3 - Discuss how you would maintain the implementation
J.4 - How could you enhance the solution in the future
K - Submission (DUE)